## Product_Backlog
Develop/Implement/Feature | # of Days(Estimate) | User Story | Status | Owner | Notes | Status Options: | Done | Partial | None
Features
a. |  |  | Done | Hannah/Damola
b. |  |  | Done | Hannah/Damola
c. |  |  | Done | Damola
Video Splitter |  | 1a | None | Damola
Show select video dialog |  | 1a | None | Damola
Show select output folder dialog |  | 1a | None | Damola
Show processing screen |  | 1a | None | Damola
Open output folder |  | 1a | None | Damola
Video Modifer |  | 1b | None | Damola
Prompt for folder containing pics to modify |  | 1b | None | Damola
Prompt for modification folder |  | 1b | None | Damola
Display modification options |  | 1b | None | Damola
Modify and show progress |  | 1b | None | Damola
Save to modification folder |  | 1b | None | Damola
Video Reassembler |  | 1c | None | Damola
Prompt for folder to reassemble |  | 1c | None | Damola
Prompt for reassemble location |  | 1c | None | Damola
Prompt for frame rate |  | 1c | None | Damola
Show progress while reassembling |  | 1c | None | Damola
Save and open reassemble location |  | 1c | None | Damola
Play in new WPF window |  | 1c | None | Damola

## User_Story_Progress
User | Story | Status | Complexity | %Complete | Story Verifed By | Notes | Status Options: | Done | Partial | None
1. VideoSplitter User
a. | I should be able to split a video | None | High
b. | I should be able to modify a video | None | High
c. | I should be able reassemble and watch the modifed video | None | High
Priority Item

## Sprint_Schedule
|  |  |  | Status Options: | Done | Partial | None
Tasks | Start Date | Duration(days) | End Date | Status
Sprint 0 (Set Up & Planning) | 2013-08-07 | 1 | 2013-08-08 | Partial
Mock Up | 2013-08-07 | 0.25 | 2013-08-07 06:00 | Done
User Stories | 2013-08-07 | 0.25 | 2013-08-07 06:00 | Done
Data Model | 2013-08-07 | 0.25 | 2013-08-07 06:00 | Done
Schedule & Planning | 2013-08-07 | 1 | 2013-08-08 | Partial
Sprint 1 (Program Manager Capabilities) | 2013-08-08 | 1 | 2013-08-09
Sprint Planning | 2013-08-08 | 1 | 2013-08-09 | None
Requirements Specification | 2013-08-08 | 1 | 2013-08-09 | None
Architecture\Design | 2013-08-08 | 1 | 2013-08-09 | None
Video Splitter | 2013-08-08 | 1 | 2013-08-09 | None
Show select video dialog | 2013-08-08 | 1 | 2013-08-09 | None
Show select output folder dialog | 2013-08-08 | 1 | 2013-08-09 | None
Show processing screen | 2013-08-08 | 1 | 2013-08-09 | None
Open output folder | 2013-08-08 | 1 | 2013-08-09 | None
Video Reassembler | 2013-08-08 | 1 | 2013-08-09 | None
Prompt for folder to reassemble | 2013-08-08 | 1 | 2013-08-09 | None
Prompt for reassemble location | 2013-08-08 | 1 | 2013-08-09 | None
Prompt for frame rate | 2013-08-08 | 1 | 2013-08-09 | None
Show progress while reassembling | 2013-08-08 | 1 | 2013-08-09 | None
Save and open reassemble location | 2013-08-08 | 1 | 2013-08-09 | None
Play in new WPF window | 2013-08-08 | 1 | 2013-08-09 | None
Unit\Regression Testing | 2013-08-08 | 1 | 2013-08-09 | None
Usability testing\Deployment\Security Review\Refactoring | 2013-08-08 | 1 | 2013-08-09 | None
Milestone 1 (Able to split video, Able to reassemble video) | 2013-08-08 | 1 | 2013-08-09 | None
Sprint 2 (Associate Profile) | 2013-08-09 | 1 | 2013-08-10
Sprint Planning | 2013-08-09 | 1 | 2013-08-10 | None
Requirements Specification | 2013-08-09 | 1 | 2013-08-10 | None
Architecture\Design | 2013-08-09 | 1 | 2013-08-10 | None
Profile Manager | 2013-08-09 | 1 | 2013-08-10 | None
View Profile | 2013-08-09 | 1 | 2013-08-10 | None
Unit\Regression Testing | 2013-08-09 | 1 | 2013-08-10 | None
Usability testing\Deployment\Security Review\Refactoring | 2013-08-09 | 1 | 2013-08-10 | None
Milestone 1 ( Demo Program Manager, Associate Profile Capabilities) | 2013-08-09 | 1 | 2013-08-10 | None
Sprint 3 (TBD) | 2013-08-10 | 1 | 2013-08-11
Sprint Planning | 2013-08-10 | 1 | 2013-08-11 | None
Requirements Specification | 2013-08-10 | 1 | 2013-08-11 | None
Architecture\Design | 2013-08-10 | 1 | 2013-08-11 | None
Feature Development | 2013-08-10 | 1 | 2013-08-11 | None
Unit\Regression Testing | 2013-08-10 | 1 | 2013-08-11 | None
Usability testing\Deployment\Security Review\Refactoring | 2013-08-10 | 1 | 2013-08-11 | None
Sprint 4 (TBD) | 2013-08-11 | 1 | 2013-08-12
Sprint Planning | 2013-08-11 | 1 | 2013-08-12 | None
Requirements Specification | 2013-08-11 | 1 | 2013-08-12 | None
Architecture\Design | 2013-08-11 | 1 | 2013-08-12 | None
Feature Development | 2013-08-11 | 1 | 2013-08-12 | None
Unit\Regression Testing | 2013-08-11 | 1 | 2013-08-12 | None
Usability testing\Deployment\Security Review\Refactoring | 2013-08-11 | 1 | 2013-08-12 | None
Milestone 2 (TBD) | 2013-08-11 | 1 | 2013-08-12 | None
Formulas:
End Date = [Start Date]+[Duration(days)]

## To-Do
To-Do
Make deployable and accessible from webserver
Documentation and usage doc
Github commit